## PSP0 Project Plan Summary form
/Non Project/PSP Fundamentals & Advanced/Program 1
PSP0 Project Plan Summary
Project Owner | Fredy Benavides Gordillo
Start Date | feb 05, 2017 09:44:27 AM
Completion Date | feb 06, 2017 08:49:22 AM |  |  |  | Completed: *
Keywords
Language | Java
Time in Phase (min.) | Plan | Actual | To Date | To Date %
Planning |  | 0.018056 | 0.018056 | 14.4%
Design |  | 0.018056 | 0.018056 | 14.4%
Code |  | 0.066667 | 0.066667 | 53.3%
Compile |  | 0.013194 | 0.013194 | 10.6%
Test |  | 0.0048611 | 0.0048611 | 3.89%
Postmortem |  | 0.0041667 | 0.0041667 | 3.33%
Total | 0.10417 | 0.125 | 0.125
Defects Injected |  | Actual | To Date | To Date %
Before Development |  | 0 | 0 | 0%
Planning |  | 0 | 0 | 0%
Design |  | 2 | 2 | 40%
Code |  | 3 | 3 | 60%
Compile |  | 0 | 0 | 0%
Test |  | 0 | 0 | 0%
Total Development |  | 5 | 5
Defects Removed |  | Actual | To Date | To Date %
Planning |  | 0 | 0 | 0%
Design |  | 0 | 0 | 0%
Code |  | 3 | 3 | 60%
Compile |  | 2 | 2 | 40%
Test |  | 0 | 0 | 0%
Total Development |  | 5 | 5
After Development |  | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.